LMS PLATFORM

Work Breakdown Structure, Roadmap & Implementation Plan

Keycloak SSO  ·  .NET Aspire Microservices

Version 1.0

April 2026

# Table of Contents

# 1. Executive Summary

This document provides the complete Work Breakdown Structure (WBS), implementation roadmap, and project plan for the LMS platform — a cloud-native Learning Management System built on .NET Aspire microservices with Keycloak as the identity and SSO provider.

The platform is designed across four phases spanning approximately 24 two-week sprints (12 months). It covers 10 major feature domains comprising 60+ individual work packages, progressing from foundational infrastructure through core learning services, AI-powered capabilities, enterprise compliance, and advanced differentiating features.

## 1.1 Scope overview

- 10 major work breakdown domains (WBS Level 1)

- 60+ individual work packages across 4 delivery phases

- Team of 11 FTEs across 7 roles

- Technology stack: .NET 9, Aspire, YARP, Keycloak, MassTransit, RabbitMQ, PostgreSQL, Redis, MongoDB, Semantic Kernel

- Delivery model: 2-week sprints, event-driven microservices, feature-flagged rollout

## 1.2 Phase summary

| Phase | Name | Key deliverables | Duration | Sprints |
| --- | --- | --- | --- | --- |
| Phase 1 | Foundation & Core | Infrastructure, SSO, core learning services, basic assessment, notifications | Q1–Q2 (16w) | Sprints 1–8 |
| Phase 2 | Learning Intelligence | Gamification, adaptive assessment, AI tutor, live sessions, payments, analytics | Q3–Q4 (16w) | Sprints 9–16 |
| Phase 3 | Enterprise & Scale | Marketplace, skills, peer learning, GDPR, white-label, DRM, predictive AI | Q5–Q6 (14w) | Sprints 17–23 |
| Phase 4 | Innovation | Virtual labs, blockchain credentials, engagement AI, AI translation | Q7–Q8 (4w) | Sprints 24+ |

# 2. Work Breakdown Structure (WBS)

Each work package (WP) is defined with a unique ID, name, primary deliverable, estimated effort, responsible role, and target phase. Effort is in calendar weeks assuming a single engineer unless noted.

| ID | Work package | Primary deliverable | Effort | Owner role | Phase |
| --- | --- | --- | --- | --- | --- |
| 1.0 | INFRASTRUCTURE & FOUNDATION |  |  |  |  |
| 1.1 | Keycloak SSO setup | Realm, clients, OIDC config | 2w | DevOps | Phase 1 |
| 1.2 | Aspire AppHost scaffold | Solution structure, CI/CD | 1w | Lead Dev | Phase 1 |
| 1.3 | YARP API Gateway | Routing, JWT middleware | 1w | Backend | Phase 1 |
| 1.4 | Service defaults & telemetry | OpenTelemetry, health checks | 1w | Lead Dev | Phase 1 |
| 1.5 | Database provisioning | PostgreSQL, Redis, MongoDB | 1w | DevOps | Phase 1 |
| 1.6 | Event bus (RabbitMQ) | MassTransit, contracts lib | 1w | Backend | Phase 1 |
| 1.7 | Feature flags | Azure App Config integration | 0.5w | Lead Dev | Phase 1 |
| 2.0 | CORE LEARNING SERVICES |  |  |  |  |
| 2.1 | Identity service | Auth, roles, multi-tenant | 2w | Backend | Phase 1 |
| 2.2 | Course service | CRUD, catalog, versioning | 3w | Backend | Phase 1 |
| 2.3 | Content delivery service | Video, PDF, S3, CDN, HLS | 3w | Backend | Phase 1 |
| 2.4 | Enrollment service | Seats, waitlist, billing hook | 2w | Backend | Phase 1 |
| 2.5 | Progress service (xAPI) | Tracking, completion, xAPI | 3w | Backend | Phase 1 |
| 2.6 | Notification worker | Email, push, SMS via bus | 1.5w | Backend | Phase 1 |
| 3.0 | ASSESSMENT & GRADING |  |  |  |  |
| 3.1 | Assessment service | Quiz engine, question bank | 3w | Backend | Phase 1 |
| 3.2 | Adaptive assessment engine | IRT theta, difficulty bands | 2w | Backend | Phase 2 |
| 3.3 | LLM auto-grading | Short answer + rubric AI | 2.5w | AI Team | Phase 2 |
| 3.4 | Plagiarism detection | pgvector + Copyleaks webhook | 2w | Backend | Phase 2 |
| 3.5 | Grade appeal workflow | Audit trail, instructor review | 1w | Backend | Phase 2 |
| 4.0 | AI-POWERED LEARNING |  |  |  |  |
| 4.1 | Recommendation service | Knowledge graph, mastery, CF | 3w | AI Team | Phase 2 |
| 4.2 | AI tutor / RAG chatbot | Semantic Kernel, pgvector | 3w | AI Team | Phase 2 |
| 4.3 | AI course generator | Outline → lessons → quizzes | 3w | AI Team | Phase 3 |
| 4.4 | Engagement AI | Frustration/boredom detection | 2w | AI Team | Phase 4 |
| 4.5 | AI-assisted content authoring | Block editor, quiz generator | 2w | AI Team | Phase 3 |
| 4.6 | Auto caption (Whisper) | Video caption generation | 1w | AI Team | Phase 3 |
| 5.0 | GAMIFICATION |  |  |  |  |
| 5.1 | Points & XP engine | Leaderboard, Redis sorted set | 1.5w | Backend | Phase 2 |
| 5.2 | Streak & check-in system | Freeze tokens, grace period | 1w | Backend | Phase 2 |
| 5.3 | Tasks & daily missions | Repeatable, deadline-aware | 1w | Backend | Phase 2 |
| 5.4 | Goals (multi-step) | Progress bar, instructor-set | 1w | Backend | Phase 2 |
| 5.5 | Badges & achievements | Rules engine, rarity tiers | 1.5w | Backend | Phase 2 |
| 5.6 | SignalR live badge pop-ups | Real-time frontend events | 0.5w | Frontend | Phase 2 |
| 6.0 | SOCIAL & LIVE LEARNING |  |  |  |  |
| 6.1 | Live session service | Zoom webhook, attendance | 2w | Backend | Phase 2 |
| 6.2 | Recording ingestor | Download → ContentService | 1w | Backend | Phase 2 |
| 6.3 | Discussion forums | Threaded, per-course | 2w | Full-stack | Phase 2 |
| 6.4 | Peer review system | Rubric scoring, assignment | 2w | Full-stack | Phase 3 |
| 6.5 | Study groups & cohorts | Capped groups, shared goals | 1.5w | Full-stack | Phase 3 |
| 6.6 | Mentor pairing | Advanced + beginner matching | 1w | Backend | Phase 3 |
| 7.0 | BUSINESS & MONETISATION |  |  |  |  |
| 7.1 | Payment service | Stripe subscriptions, plans | 2w | Backend | Phase 2 |
| 7.2 | Marketplace service | Course listing, ratings | 2.5w | Full-stack | Phase 3 |
| 7.3 | Revenue sharing | Stripe Connect, payouts | 1.5w | Backend | Phase 3 |
| 7.4 | Coupon & promotions engine | Flash sales, bundles | 1w | Backend | Phase 3 |
| 7.5 | Certificate service | Open Badges 3.0, verify URL | 2w | Backend | Phase 2 |
| 7.6 | Skills & competency framework | Taxonomy, skill passport | 2.5w | Backend | Phase 3 |
| 8.0 | ANALYTICS & REPORTING |  |  |  |  |
| 8.1 | Analytics worker (CQRS) | Event projections, ClickHouse | 2w | Backend | Phase 2 |
| 8.2 | Instructor dashboards | Completion, engagement funnels | 2w | Full-stack | Phase 2 |
| 8.3 | Predictive at-risk detection | ML model, early warning | 2.5w | AI Team | Phase 3 |
| 8.4 | Org-level BI & data export | S3 export, Power BI embed | 1.5w | Backend | Phase 3 |
| 8.5 | Skill gap analysis dashboard | Org admin reports | 1w | Full-stack | Phase 3 |
| 9.0 | COMPLIANCE, SECURITY & ENTERPRISE |  |  |  |  |
| 9.1 | GDPR service | Erasure, export API | 2w | Backend | Phase 3 |
| 9.2 | Audit log service | Immutable EventStore append | 1.5w | Backend | Phase 3 |
| 9.3 | SCORM/xAPI/cmi5 compliance | Standards adapter layer | 2w | Backend | Phase 2 |
| 9.4 | Content DRM | Signed URLs, watermark PDF | 1.5w | Backend | Phase 3 |
| 9.5 | White-label & multi-tenant | Custom domain, theme engine | 3w | Full-stack | Phase 3 |
| 9.6 | Mandatory training tracking | Deadlines, compliance alerts | 1w | Backend | Phase 3 |
| 10.0 | ADVANCED FEATURES |  |  |  |  |
| 10.1 | Offline / PWA mode | Service worker, sync engine | 2.5w | Full-stack | Phase 3 |
| 10.2 | Virtual lab service | k8s ephemeral containers | 3w | DevOps/Dev | Phase 4 |
| 10.3 | Digital credentials (blockchain) | Open Badges + chain anchor | 2w | Backend | Phase 4 |
| 10.4 | Accessibility & i18n | WCAG 2.1 AA, RTL, AI translate | 2w | Full-stack | Phase 3 |
| 10.5 | AI translation service | Course multilingual publish | 1.5w | AI Team | Phase 4 |

* Effort estimates assume one senior engineer per package. Parallel execution across 3 backend engineers compresses Phase 1–2 calendar time significantly.

# 3. Roadmap — Sprint Gantt

The chart below maps each feature stream to sprints (S1–S24). Each sprint is 2 weeks. Coloured bars represent active development; colour denotes phase.

|  | Phase 1 — Foundation |  | Phase 2 — Intelligence |  | Phase 3 — Enterprise |  | Phase 4 — Innovation |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Feature / Service | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Quarter | Q1 |  |  |  |  |  | Q2 |  |  |  |  |  | Q3 |  |  |  |  |  | Q4 |  |  |  |  |  |
| 1. Infrastructure & Foundation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Core Learning Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Assessment & Grading (basic) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. Gamification Engine |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Live Sessions & Forums |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. Analytics Worker (CQRS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. Payment & Certificates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. Adaptive Assessment (IRT) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. AI Tutor / RAG Chatbot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10. Recommendation Service |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11. Plagiarism Detection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12. Marketplace & Revenue Split |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13. Skills & Competency |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14. Peer Review & Cohorts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15. GDPR & Compliance Service |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 16. White-label Multi-tenant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17. Content DRM & Security |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18. Predictive At-risk AI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 19. AI Course Generator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 20. Offline PWA Mode |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 21. Accessibility & i18n |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 22. Virtual Lab Service |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 23. Engagement / Wellbeing AI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 24. Blockchain Credentials |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 25. AI Translation Service |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# 4. Detailed Phase Implementation Plan

## Phase 1 — Foundation & Core (Sprints 1–8)

Goal: deliver a working LMS skeleton — students can register, browse courses, watch content, track progress, and complete basic assessments. All infrastructure is production-ready from day one.

### Sprint 1–2: Infrastructure

- Stand up Keycloak container in Aspire AppHost with realm-export.json auto-import

- Scaffold all Aspire projects: AppHost, ServiceDefaults, Contracts, Gateway (YARP)

- Configure OpenTelemetry → Aspire Dashboard; health check endpoints on all services

- Provision PostgreSQL (+ pgvector extension), Redis, MongoDB, RabbitMQ via Aspire containers

- Set up GitHub Actions CI: build → test → push → deploy to staging

- Feature flag baseline with Azure App Configuration

### Sprint 3–4: Identity, Course & Enrollment

- Identity service: Keycloak JWT validation, role claims (student/instructor/admin/org-admin)

- Course service: catalog CRUD, module/lesson hierarchy, prerequisites, course versioning

- Enrollment service: seat management, waitlist, PaymentService hook (stubbed)

- YARP gateway: per-role route policies, X-User-Id / X-Roles header propagation

### Sprint 5–6: Content Delivery & Progress

- Content service: S3 upload, MongoDB metadata, video transcoding pipeline (async HLS)

- CDN integration (CloudFront signed URLs, short TTL)

- Progress service: lesson completion tracking, xAPI statement emitter, watch-time events

- Notification worker: email templates (SendGrid), MassTransit consumer wired to all core events

### Sprint 7–8: Assessment & Stabilisation

- Assessment service: question bank, quiz CRUD, timed session with Redis state, auto-grading (MCQ)

- Certificate worker: PDF generation on CourseCompleted event

- Integration test suite: per-service + cross-service scenario tests

- Load test baseline: k6 scripts for enrollment flow, content delivery, quiz submission

- Phase 1 review & bug fix sprint buffer

## Phase 2 — Learning Intelligence (Sprints 9–16)

Goal: elevate the platform with AI, gamification, live learning, payments, and analytics. The platform becomes meaningfully differentiated in this phase.

### Sprint 9–10: Gamification & Payments

- GamificationService: points/XP engine, streak/check-in (Redis), tasks, goals, achievements rules engine

- Redis leaderboard (ZADD sorted sets); SignalR hub for live badge pop-ups

- PaymentService: Stripe subscriptions, webhook handler, plan tier enforcement in Enrollment

- SCORM 2004 / xAPI / cmi5 compliance adapter layer on ContentService

### Sprint 11–12: Live Sessions & Analytics

- LiveSessionService: Zoom/Google Meet webhook handler, attendance tracker, recording ingestor

- AnalyticsWorker: CQRS event projections → ClickHouse (or TimescaleDB)

- Instructor dashboard: completion funnels, watch-time heatmaps, quiz score distributions

- Discussion forum service: threaded comments, per-course namespace, moderation queue

### Sprint 13–14: Adaptive Assessment & Plagiarism

- Adaptive session engine: IRT theta tracking in Redis, difficulty band selector, question randomisation

- PlagiarismWorker: internal cosine similarity via pgvector; Copyleaks/Turnitin webhook integration

- Grade appeal workflow: instructor review queue, audit trail, student notification on decision

### Sprint 15–16: AI Tutor & Recommendation

- RecommendationService: knowledge graph per learner (PostgreSQL adjacency list), mastery scoring, spaced repetition scheduler

- AI Tutor: Semantic Kernel RAG pipeline; per-course vector namespace in pgvector; Socratic mode prompt chain

- LLM auto-grading: short-answer rubric scoring via Anthropic/OpenAI API; instructor review gate before release

- Phase 2 review, performance tuning, A/B test setup for recommendation quality

## Phase 3 — Enterprise & Scale (Sprints 17–23)

Goal: unlock B2B and enterprise sales. Multi-tenancy, marketplace, compliance, and advanced analytics make the platform enterprise-grade.

### Sprint 17–18: Marketplace & Revenue

- MarketplaceService: course listing, search (Elasticsearch), ratings/reviews, curator approval flow

- Revenue sharing: Stripe Connect instructor accounts, configurable split, nightly payout worker

- Coupon/promotions engine: flash sales, bundle pricing, org-bulk licensing

- SkillsService: SFIA-compatible taxonomy, course-to-skill mapping, learner skill passport (JSON-LD)

### Sprint 19–20: Peer Learning & Social

- Peer review system: rubric builder, blind/open assignment modes, reviewer assignment algorithm

- Study groups: learner-created, capped, shared goal tracking, group leaderboard

- Mentor pairing: matching algorithm (mastery score delta), session scheduling, feedback loop

- AI course generator: outline → lesson → quiz pipeline; instructor review & publish gate

### Sprint 21–22: Compliance & Security

- GDPR service: right-to-erasure (soft delete + anonymisation), data export API (JSON/CSV)

- Audit log service: append-only EventStoreDB projection; SOC 2 evidence S3 bucket

- Content DRM: signed URL rotation, PDF watermarking (user ID embedded), device-limit enforcement

- White-label: per-tenant custom domain (automated SSL via cert-manager), theme engine (logo/palette/font)

- Mandatory training tracking: deadline manager, compliance dashboard, auto-escalation alerts

### Sprint 23: AI & Accessibility

- Predictive at-risk detection: ML model (completion rate + engagement + score trends) → instructor nudge

- WCAG 2.1 AA audit + remediation across all frontends

- Auto-caption generation: Whisper model deployed as k8s job, triggered on video upload

- RTL layout support (Arabic, Hebrew); i18n string extraction for all UI surfaces

## Phase 4 — Innovation (Sprint 24+)

Goal: deliver market-differentiating features that establish the platform as a next-generation LMS.

- Virtual lab service: Kubernetes ephemeral pod provisioner, browser-based VS Code (code-server), automated lab validation scripts, TTL enforcement

- Blockchain credentials: Open Badges 3.0 JWT issuance, optional on-chain anchoring (Polygon), LinkedIn auto-share, public /verify/{hash} endpoint

- Engagement / wellbeing AI: frustration/boredom signal detection from interaction patterns; automatic difficulty-pace adjustment; instructor weekly digest

- AI translation service: GPT-4 batch translation of lesson text + auto-subtitle generation; instructor review before publishing multilingual variant

# 5. Team Structure & Velocity

## 5.1 Team composition

| Role | FTEs | Responsibilities |
| --- | --- | --- |
| Lead Architect / Dev | 1 | System design, Aspire AppHost, gateway, code review |
| Backend Engineers | 3 | Microservices, event bus, domain logic, APIs |
| AI / ML Engineers | 2 | RAG, recommendation, adaptive assessment, LLM grading |
| Full-stack Engineers | 2 | BFF layers, instructor UI, learner dashboard |
| DevOps / Platform | 1 | k8s, CI/CD, Keycloak, infra-as-code, monitoring |
| QA Engineer | 1 | Test automation, integration tests, load testing |
| Product / UX | 1 | Specs, wireframes, acceptance criteria, user testing |

## 5.2 Velocity assumptions

- Sprint velocity: 40 story points per backend engineer per 2-week sprint

- Work packages estimated at 1–3 sprints of single-engineer effort

- 3 backend engineers allow parallel execution; Phase 1 calendar time reduced from 24 to 8 weeks

- AI team operates on separate track; spikes allowed for model evaluation in sprints 7–8

- 20% buffer built into each phase for QA, bug fixing, and sprint review feedback

# 6. Risk Register

| ID | Risk | Impact | Probability | Mitigation strategy |
| --- | --- | --- | --- | --- |
| R1 | Keycloak realm misconfiguration | High | Medium | Test auth flows in CI; pre-import realm JSON |
| R2 | AI service latency / cost overrun | High | High | Cache embeddings; use async endpoints; set budget alerts |
| R3 | Multi-tenant data leakage | Critical | Low | EF Core global filters + integration test suite per tenant |
| R4 | Video transcoding bottleneck | Medium | Medium | Async queue; auto-scale transcoder pods; CDN pre-warm |
| R5 | Scope creep (feature additions) | High | High | Feature flags gate all Tier 3/4 work; strict sprint review |
| R6 | Plagiarism provider API downtime | Low | Medium | Fallback to internal pgvector similarity only; retry queue |
| R7 | k8s lab pod resource exhaustion | Medium | Low | TTL enforcement; resource quotas per namespace |
| R8 | GDPR deletion breaking audit trail | High | Low | Soft delete + anonymisation; never hard-delete audit log |

# 7. Definition of Done

Each work package is considered complete when ALL of the following criteria are met:

## 7.1 Code quality

- All unit tests pass with minimum 80% line coverage

- Integration tests cover the happy path and at least 2 error scenarios

- No Sonar critical/blocker findings outstanding

- Code reviewed and approved by at least one senior engineer

## 7.2 Observability

- Service emits structured logs with CorrelationId and TenantId on every request

- OpenTelemetry traces visible in Aspire Dashboard for all HTTP calls and DB queries

- Health check endpoint returns 200 with dependency status

- Alert rule configured in Prometheus for p99 latency > 500ms and error rate > 1%

## 7.3 Security

- JWT validation via Keycloak JWKS confirmed with negative test (expired/tampered token → 401)

- All secrets injected via environment variable / Azure Key Vault — no hardcoded credentials

- RBAC role enforcement tested: unauthenticated and wrong-role requests return 403

## 7.4 Infrastructure

- Service deployable via aspire publish → Docker Compose (local) and ACA/AKS (staging)

- Database migrations run automatically on startup; rollback script exists

- Feature flag gate implemented for any Tier 3/4 capability

## 7.5 Documentation

- OpenAPI spec generated and published to developer portal

- ADR (Architecture Decision Record) written for any significant design choice

- Runbook entry updated with new service's common failure scenarios and recovery steps

# 8. Success Metrics & KPIs

| Metric | Phase 1 target | Phase 2 target | Phase 3 target | Measurement |
| --- | --- | --- | --- | --- |
| Course completion rate | — | > 65% | > 75% (AI-assisted paths) | Analytics worker projection |
| API p99 latency | < 300 ms | < 300 ms | < 300 ms | Prometheus p99 histogram |
| Daily active learners | Baseline established | 20% WoW growth | Stable retention > 60% | AnalyticsWorker DAU query |
| Streak engagement rate | — | > 40% learners active streak | > 50% | GamificationService events |
| AI tutor satisfaction | — | CSAT > 4.0/5.0 | CSAT > 4.3/5.0 | Post-session rating widget |
| System uptime | 99.5% | 99.9% | 99.95% | Prometheus uptime monitor |

Document prepared by: Architecture & Product Team  |  Classification: Confidential  |  Review cycle: Quarterly